## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2231-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | 2235-SWEN-261-03-1a-albatross
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a helper I want to see a list of needs so that I choose what to contribute to. | Given that I am on the u-fund site when I am not on the Needs page then I must see a means to navigate to the Needs page. | ✅ | AL - Pass
| Given that I am not on the Needs page when I choose the Needs page then I am taken to the Needs page. | ✅ | AL - Pass
| Given that I am on the Needs page when there are no needs in the cupboard I see a message indicating that that there are no needs available to contribute. | ✅ | AL - Pass
| Given that I am on the Needs page when there are needs in the cupboard then I see each need and short description. | ✅ | AL - Pass ; Clicking the Need -> Views Name/Price/Type
| Given that I am on the Needs page when there are needs in the cupboard then I see a means to add each need to my funding basket. | ✅ | AL - Pass
AS a User I WANT to submit a request to get the the requests in the mailbox whose name contains the given text, SO THAT I have access to only that subset of requests. | Given I am a user and I submit a request to search the mailbox for requests whose title contains a given text, When matches exist in the mailbox, Then the system should return a list of requests that contain the given text in their titles and a status code of 200 (OK). |  |  | ✅ | AL - Fail - 4/8 : "No search area implemented yet"
| Given I am a user and I submit a request to search the mailbox for requests whose title contains a given text, When no matches exist in the mailbox, Then the system should return an empty list of requests and a status code of 200 |  |  | ✅ | AL - Fail - 4/8 : "No search area implemented yet"
| Given I am a user and I submit a request to search the mailbox for requests that have a completed status, When matches exist in the mailbox, Then the system should return an list of requests that have that completed status and a status code of 200 |  |  | ✅ | AL - Fail - 4/8 : "No search area implemented yet"
| Given I am a user and I submit a request to search the mailbox for requests that have a completed status, When no matches exist in the mailbox, Then the system should return an empty list of requests and a status code of 200 |  |  | ✅ | AL - Fail - 4/8 : "No search area implemented yet"
| Given I am a user and I submit a request to search the mailbox for requests that I made, When matches exist in the mailbox, Then the system should return a list of requests that I created and a status code of 200 (OK). |  |  | ✅ | AL - Fail - 4/8 : "No search area implemented yet"
| Given I am a user and I submit a request to search the mailbox for requests I have created, When no matches exist in the mailbox, Then the system should return an empty list of requests and a status code of 200 |  |  | ✅ | AL - Fail - 4/8 : "No search area implemented yet"
| Given I submit a request for searching the mailbox's requests, When the system successfully processes the request, Then each request in the returned list should include at least the request's author, description, and a completed status. |  |  | ✅ | AL - Fail - 4/8 : "No search area implemented yet"
AS a User I WANT to have the ability to update requests I have made SO THAT I can have the request meet more of what I need. | GIVEN I submit a request to update a request WHEN I have created a request THEN I should be able update the an individual request I have made and return a status code of 200 (OK) |  |  | ✅ | AL - Fail - 4/8 : "No way to modify a request after it's sent"
| GIVEN I submit a request to update a request WHEN I have created no requests THEN the system should return a message saying that no requests exist and a status code of 200 (OK) |  |  | ✅ | AL - Fail - 4/8 : "No way to modify a request after it's sent"
AS a Helper I WANT to submit a request to create a new request (request string, completed boolean) SO THAT it is added to the list of requests. | GIVEN I submit a request object WHEN I encounter an issue THEN the system should create the request, add it to the mailbox, save to the persistent storage, and return the request object and a status code of 201 (CREATED) |  |  | ✅ | AL - Pass - 4/8
| Given I submit a help request when I encounter an issue then the system should send the request to the managers |  |  | ✅ | AL - Pass - 4/8
As a Helper, I want to be able to come back to the needs that I plan to contribute to, at another time, so that I'm not rushed with my decision. | Given that I have needs in my funding basket when I click 'logout' then my needs should stay in the funding basket to come back to another time. |  |  | ✅ | AL - Pass - 4/8
As a U-fund Manager, I don't want to see the funding baskets of users so that their privacy is respected. | Given I am a U-Fund Manager when I browse Manager UI then no Funding Baskets should be shown. |  |  | ✅ | AL - Pass - 4/8
AS a helper I WANT to be able to sign in SO THAT I can view the needs that I am able to help with. | Given I am a Helper when I login then the system should show the alternate version of the website for helpers. | ✅ | AL - Pass
AS a Admin I WANT to be able to sign into the website SO THAT I can update the cupboard and make changes. | Given I am a U-Fund Manager when I login then the system will open the website in the 'managers' view so that the manager can edit things such as the cupboard. | ✅ | AL - Pass
AS a new-user I WANT to create a new user (name, id, password) SO THAT I am able to log in. | Given I am a new-user and I'm on the login page, WHEN I click the Register button THEN I move to the User page. |  |  | ✅ | AL - Fail - 4/8 : "No registration page created, new users are created through the same input of Login"
| Given I just created a new user and I'm back on the login page, WHEN I try logging in with my specified Username + Password THEN I move to the User page. |  |  | ✅ | AL - Fail - 4/8 : "No registration page created, new users are created through the same input of Login"
As a Helper, I want to be able to “checkout” the needs that I plan to contribute to, so that I can fund them. | Given I have needs in my funding basket when I hit 'checkout' then I expect the screen to change notifying me of my donations and my funding basket will empty. |  |  | ✅ | AL - Pass - 4/8
| Given empty funding basket when I hit 'checkout' then I expect a pop-up saying "Empty Basket". |  |  | ✅ | AL - Pass - 4/8
| Given I have selected a/multiple need(s) when I go into checkout then I expect to see the need(s) I have selected. |  |  | ✅ | AL - Pass - 4/8
As a User, I WANT to be able to view donation statistics so that I know how much I've donated so far. | Given that I visit my funding basket, when I have already donated before, then I should see my total donated amount so far. |  |  | ✅ | AL - Pass - 4/8
AS a U-fund Manager I WANT to be able to respond to help requests sent by users SO THAT I can answer/help user inquires. | Given a help request has been submitted when a helper has an issue then a manager should be able to reply and change the completed status of the request. |  |  | ✅ | AL - Pass - 4/8